## Sheet1
12-01-2024 - Activity
| Module | Sub-module | Task | Responsibility | Status
| Development | Validator 1 | There will option of Approve,Reject & revert with comment in front of all question.(If question is approved the approve tab color changes to green, for reject its red & for revert with comment color is yellow.) | Praveen | Discussion Point
|  |  | Discussion on submission status & action. | Rahul | Discussion Point
|  | Super Admin | When creating a question, the Priority option is displayed as Ranking/Priority. | Avlok | Completed
|  | Question Master | Correct spelling of Question title. | Rituraj | Completed
|  | Validator 1 | Working on V1 | Avlok | WIP
|  | Validator 2 | Working on V2 | Avlok | WIP
|  | User Management | A new user will be added with unique number(0-9) | Rituraj | Completed
|  | Feedbacks | Load time issue needs to be resolved. |  | WIP
|  | Feedbacks(City Official) | There were issues while attempting a question of "Planning and Regulation" sector and it was not getting auto saved. Also, the progress bars on the side panel were not getting updated | Praveen | WIP
|  |  | There were slight alignment issues in the city official side like the buttons of file uploaded and remark added etc | Praveen | WIP
|  |  | There should be only pdf, excel, doc and Shape file in the upload file option on the city side | Rituraj | Completed
|  |  | If a city is filling any other datatype instead of the correct input type, a small error message should appear at the bottom of each input cell | Rituraj | Completed
|  |  | Only revert with comment sector will be displayed. | Praveen | WIP
|  |  | Working on validation cycle. | Praveen | WIP
|  |  | Progress bar of housing. | Avlok | Completed
|  |  | Submission date will be there when city will submit data. | Praveen | WIP
|  | Feedbacks(V1) | There will be a message in pop up form Are you sure you want to sent to V1? | Avlok | Completed
|  |  | There will be a back button for V1 &V2 dashboard. | Avlok | Completed
|  |  | Replace Submission Status with Validation Status. | Avlok | Completed
|  | Feedbacks(Super Admin) | Remove same cities from My Jobs(City Status) | Avlok | WIP
|  |  | The user ID for each city should be its name, while the unique code for every city can be managed on the backend. | Rahul | WIP
|  | Feedbacks on v1 | On filter, change the title not attempted as not validated. | Avlok | WIP
|  |  | While bookmarking a question, a popup message will appear as change the message. | Praveen | WIP
|  |  | On non reverted question there will be no action. | Avlok | WIP
|  |  | As status of V2 is submitted instead of not started show inprogress. | Avlok | WIP
|  | Feedbacks on v2 | Revert with comment not showing. | Praveen | WIP
|  |  | Change the name of button back to city as send to city. | Avlok | WIP