## Sheet1
Points | Status | Remark | ETA | Owner
1. UOM to be introduced as an extra field while adding a question which will be visible to user in i button | Done
2. Order of the inputs while creating question should be changed | Done | Rahul to provide ordering |  | Rahul
3. Two times clicking required while uploading a document for the status of question to be updated | In progress |  | EOD
4. Keep Label ,discription and supporting document of the questions should be editable even after publishing | Done |  | EOD
5. Document should open in new tab when clicking on download | Done | Only pdf | EOD
6. Consolidated city validation status : Approved , Rejected, Reverted with cities, pending at v1, pending at v2 | Done
7. Approve & Rejected color change can be tried | Deferred
8. Extra "OK" screen while validating a question | Done
9. All the previous created question will have to be pushed on the test server | Done | Cleaning to be done at backend , question will be added by pwc
10. The outline on the child question to be changed(Design) | In progress | Kavish needs to connect with narayan
11. Multiple select type of question in child questions | Later | Select many
12. Percentage option in the child questions | Done | %
13. Rejected question NA, NF etc are still missing | In progress |  |  | Praveen
14. "Click here" in the upload file window | Done | A text to be added |  | Praveen
15. Approved data for all cities should be visible : Survey name, City , Sector, Framework, Datapoint(Question), Result | WIP | Will done once connected with Pwc DBA
16. Latitude and Longitude to be removed from mandatory | Done