## Sheet1
Kumbh website 10 day's Project Plan
Execution Start Date |  | Execution End Date | Duration day's
2023-12-11 |  | 2023-12-22 | 10 days
Team |  | QA &BA | Front End Dev | Reviewer
|  | Astha,Neelam | Meena,Akash | Avi Sir, Uphar Sir,Suraj Sir
S No. | Pages | URL's | No. of Days | Design Tentative Date | Designing Status | Assigned To | Updation of Image/Content | Final Delivery Date of Page | Testing Tentative Date | Testing Status | Level 1 (Designers will coordinate with each other & verify) | Level 2 (Astha & Neelam will review & verify) | Level 3 (Uphar Sir & Suraj Sir will review & verify) | Level 4(Avi Sir will review & verify)
1 | Home Page | https://vibescom.co.in/archive/kumbh_2025/ | 2 | 2023-12-12 | WIP | Akash |  |  | 2023-12-13
2 | About Kumbh > Introduction | https://vibescom.co.in/archive/kumbh_2025/Introduction.html | 1 | 2023-12-13 | WIP |  |  |  | 2023-12-14
3 | About Kumbh > Mythological Significance | https://vibescom.co.in/archive/kumbh_2025/mythological-significance.html |  |  | WIP
4 | About Kumbh > Astrological Significance | https://vibescom.co.in/archive/kumbh_2025/astrological-significance.html |  |  | WIP
5 | About Kumbh > Social Significance | https://vibescom.co.in/archive/kumbh_2025/social-significance.html |  |  | WIP
6 | About Kumbh > Rituals of Kumbh | https://vibescom.co.in/archive/kumbh_2025/rituals-of-kumbh.html |  |  | WIP
7 | About Kumbh > Spiritual Gurus(2 pages) | https://vibescom.co.in/archive/kumbh_2025/spiritual-gurus.html |  |  | WIP
8 | About Kumbh > Study on Kumbh | https://vibescom.co.in/archive/kumbh_2025/study-on-kumbh.html |  |  | WIP
9 | Spirituality in Kumbh > Kumbh Meaning | https://vibescom.co.in/archive/kumbh_2025/kumbh_meaning.html | 0.5 | 2023-12-14 | WIP |  |  |  | 2023-12-15
10 | Spirituality in Kumbh > Kalpavas | https://vibescom.co.in/archive/kumbh_2025/Kalpavas.html |  |  | WIP
11 | Spirituality in Kumbh > Historical Significance | https://vibescom.co.in/archive/kumbh_2025/historical_significance.html |  |  | WIP
13 | Spirituality in Kumbh > Kumbh and Administrative Marble | https://vibescom.co.in/archive/kumbh_2025/kumbh_administrative_marble.html |  |  | WIP
14 | Kumbh 2025 > Attraction |  | 1 | 2023-12-14 |  |  |  |  | 2023-12-15
15 | Kumbh 2025 > Bathing Dates |  |  | 2023-12-15 |  |  |  |  | 2023-12-16
16 | Kumbh 2025 > Making of Kumbh
17 | Kumbh 2025 > Events
18 | Kumbh 2025 > Campaign
19 | Kumbh 2025 > Campaign(Detail page)
20 | Kumbh 2025 > Do’s & Don'ts
21 | About Prayagraj > History | https://vibescom.co.in/archive/kumbh_2025/history.html | 1 | 2023-12-16 | WIP |  |  |  | 2023-12-18
19 | About Prayagraj > Places to see (2pages) | https://vibescom.co.in/archive/kumbh_2025/places-to-see.html |  |  | WIP
20 | About Prayagraj > Food & Things to do | https://vibescom.co.in/archive/kumbh_2025/food.html |  |  | WIP
21 | About Prayagraj > Nearby Attraction | https://vibescom.co.in/archive/kumbh_2025/nearby-attractions.html |  |  | WIP
| Kumbh 2019 A Tapestry > Acheivements |  | 1 | 2023-12-18 |  |  |  |  | 2023-12-19
22 | Kumbh 2019 A Tapestry > Highlights
23 | Kumbh 2019 A Tapestry > Major Attraction
24 | Gallery > Media |  | 0.5 | 2023-12-19 |  |  |  |  | 2023-12-20
25 | Gallery > Video Gallery
26 | Plan Your Travel > How to Reach > Train |  | 1 | 2023-12-19 |  |  |  |  | 2023-12-20
27 | Plan Your Travel > How to Reach > Flight |  |  | 2023-12-20 |  |  |  |  | 2023-12-21
28 | Plan Your Travel > How to Reach > Bus
29 | What’s New > Key Announcements |  | 1 | 2023-12-21 |  |  |  |  | 2023-12-22
30 | What’s New > Tenders
31 | What’s New > Downloads
32 | contact us page |  | 1 | 2023-12-22
33 | Thank you
34 | Privacy policy
35 | 404 page
10

## HTML Checklist
DESIGNING CHECKLIST
Sl No. | AREA | CHECK POINTS | Designer | Tested By | Pass/Fail/NA | REMARK
1 | COLOR/THEME/FONT/ STYLING | The color theme of website should be according to logo color matched, If logo not available> design it first or ask to your senior.
3 |  | Dummy content on the website should not be there. Try to put relevant content and approved by your peer.
4 |  | For maintenance project follow the theme and color that used previously
5 |  | maximum 2 types of a font in the single page.
6 |  | Loader would be design as per the theme
7 |  | Theme and styling should always be matched with client's business.
11 | RESPONSIVENESS/DEVICE /BROWSER | Check with client of their requirement related to maxumum resolution
1366x768/Desktop/Laptop/Chrome
12 |  | 1366x768/Desktop/Laptop/Firefox
13 |  | 1366x768/Desktop/Laptop/IE version 10
14 |  | 1366x768/Desktop/Laptop/IE version 11
15 |  | Microsoft Edge 41.16299.15.0 Microsoft EdgeHTML 16.16299
16 |  | Safari 11
17 |  | Mac 10.13.2
18 |  | iPhone 6 Plus(414x736)
19 |  | iPhone 6(375x667)
20 |  | iphoneX
21 |  | iPhone 5(320x568)
22 |  | iPad Pro(1024x1366)
23 |  | iPad(768x1024)
24 |  | Galaxy S5(360x640)
25 |  | Nexus 6P(412x732)
26 |  | Nexus 5X(412x732)
27 |  | responsiveness> If any website is not compatible with particular device > there should be clear message that "This website is not compatible with this device or version"
28 |  | Some item may be hidden in case of mobile devices
29 |  | Foreground image fit in container(Center,middle)
30 |  | Text on image then image should have grey/white shade either on image or text
31 |  | Background image it in container(Center, Middle)
32 |  | 4-5 items in one row of listing
33 |  | Items should be in slider on mobile or responsive
35 | MEDIA FILE CHECK | Video functionality (PAUSE,PLAY,STOP)
36 |  | Verified GIF
37 |  | Audio auto play
38 |  | Auto play option by default for any project
39 |  | optimization(<100Kb-banner/1920px-slider, <50kb -other, Video <1MB)
40 |  | Size(maintain ratio across website) multiple of 5 or 10 if a single image used multiple time ratio would be changed accordingly
41 |  | Alt Tag on images
Basic SEO should be cover
42 |  | width & Height multiple of 5 or 10
43 |  | Product Image upload resolution- Thumbnail, Normal, Actual
44 |  | Banner/Images < 1mb
45 |  | Image size < or = 200 KB (banner/slider 100-200 Kb , product image/service 50-100 Kb)
46 |  | image should have their appropriate nomenclature
47 |  | Use font awesome for the adaptability of website theme. Do not use the image for any icon
48 | CONTENT AND ALL LINKS | All Menu Links
49 |  | All Links (Clickable with background)
50 |  | External Links-Target : Blank
51 |  | Facebook
52 |  | Twitter
53 |  | G-Mail
54 |  | LinkedIn
55 |  | Alt Tag on links
56 | DESIGN VALIDATOR | W3C
57 |  | WEBSITE GRADOR
58 |  | GTMETRIX (check design elements)
62 |  | Alt Tag on all clickable places | ?
63 |  | No Cursor pointer (on Non Link Objects)
64 |  | Hover Effects on Links | ?
65 |  | Follow the guidelines of W3C and other popular validator
68 |  | 404 page not found